## Schedule
Project Start Date: | 2024-01-16 | [5 empty] | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12 | [6 empty] | 2024-02-19 | [6 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08
Project Name | Communications System Program | time axis 2024-01-15 to 2024-07-14
 | time axis 2024-01-15 to 2024-07-14
Activity | Assinged To | Start | End | Days | Status | %Done
Requirements
Project.init() Meeting | ALL | 2024-01-31 | 2024-01-31 |  | Complete | 100% | bar: 2024-01-31
Project.init() Presentation | ALL | 2024-02-01 | 2024-02-01 | 1 | Complete | 100% | bar: 2024-02-01
SRS Meeting | ALL | 2024-02-11 | 2024-02-11 | 0 | Complete | 100% | bar: 2024-02-11
List all requirements/use cases | ALL | 2024-02-11 | 2024-02-18 | 5 | Complete | 100% | bar: 2024-02-18
Use Case Diagram | CS | 2024-02-11 | 2024-02-28 |  | Complete | 100% | bar: 2024-02-28
Initial Class Diagram | JM | 2024-02-11 | 2024-02-28 |  | Complete | 100% | bar: 2024-02-28
Sequence Diagrams | HA, JG, LM | 2024-02-11 | 2024-02-28 | 13 | Complete | 100% | bar: 2024-02-28
SRS Presentation Meeting | ALL | 2024-02-28 | 2024-02-28 | 1 | Complete | 100% | bar: 2024-02-28
Requirements Presentation | ALL | 2024-02-29 | 2024-02-29 | 1 | Complete | 0% | bar: 2024-02-29
SRS Submital Due | ALL | 2024-02-29 | 2024-02-29 | 1 | Complete | 90% | bar: 2024-02-29
Design | [5 empty] | 0%
Initial Design Meeting | ALL | 2024-03-05 | 2024-03-05 | 1 | Complete | 100% | bar: 2024-03-05
Complete Initial Class Diagram | ALL | 2024-03-05 | 2024-03-12 |  | Complete | 100% | bar: 2024-03-12
Updated use cases | CS,HM | 2024-03-12 | 2024-03-24 |  | Complete | 100%
Updated Sequence Diagrams | JM,LM,JG | 2024-03-12 | 2024-03-24 |  | Complete | 100%
Updated SRS Meeting | ALL | 2024-03-24 | 2024-03-24 |  | Complete | 100%
Design Presentation Meeting | ALL | 2024-03-27 | 2024-03-27 |  | Complete | 100% | bar: 2024-03-27
Design Presentation | ALL | 2024-03-28 | 2024-03-28 |  | Complete | 100% | bar: 2024-03-28
Design Submital Due | ALL | 2024-03-28 | 2024-03-28 |  | In Progress | 95% | bar: 2024-03-28
Implementation / Testing ?
GUI Mock-up | CS, JM, LM | 2024-03-29 | 2024-04-05 |  | In Progress | 50% | bar: 2024-04-05
GUI/Server Implemenation Meeting | ALL | 2024-03-31 | 2024-03-31 |  | Not Started | 0% | bar: 2024-03-31
Standard/IT GUI Implementation | CS, JM, LM | 2024-04-01 | 2024-04-12 |  | Not Started | 0% | bar: 2024-04-12
Handling Messages | LM | 2024-04-01 | 2024-04-12 |  | Not Started | 0%
Notifications | LM | 2024-04-01 | 2024-04-12 |  | Not Started | 0%
GUI Layout | JM | 2024-04-01 | 2024-04-12 |  | Not Started | 0%
Client to Server Communication | CS | 2024-04-01 | 2024-04-12 | 10 | Not Started | 0% | bar: 2024-04-12
Messages Implementation | CS | 2024-04-01 | 2024-04-12 |  | Not Started | 0% | bar: 2024-04-12
Client to Server Pipeline | CS | 2024-04-01 | 2024-04-12 |  | Not Started | 0% | bar: 2024-04-12
Sever Implementation | JG, HM | 2024-04-01 | 2024-04-12 |  | Not Started | 0% | bar: 2024-04-12
ChatMessage Routing / Logging | HM | 2024-04-01 | 2024-04-12 |  | Not Started | 0%
Create Chat, getUserList(), Login + Logout flows | JG | 2024-04-01 | 2024-04-12 |  | Not Started | 0%
"Put it all together" Meeting | ALL | 2024-04-14 | 2024-04-14 |  | Not Started | 0% | bar: 2024-04-14
MVP Testing | ALL | 2024-04-15 | 2024-04-21 |  | Not Started | 0% | bar: 2024-04-21
Review Meeting | ALL | 2024-04-21 | 2024-04-21 |  | Not Started | 0% | bar: 2024-04-21
Final Presentation Meeting | ALL | 2024-05-01 | 2024-05-01 |  | Not Started | 0% | bar: 2024-05-01
Final Presentation | ALL | 2024-05-02 | 2024-05-02 |  | Not Started | 0% | bar: 2024-05-02
Final Submital Due | ALL | 2024-05-02 | 2024-05-02 |  | Not Started | 0% | bar: 2024-05-02
Maintenance
Insert above this line
STATUSES
Not Started
In Progress
Blocked
Complete
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))